## Worksheet
Home Management - Project Tracker (Manager View)
Project ID | Project Name | Description | Status | Priority | Assigned To | Budget (USD) | Scheduled Start Date | Scheduled End Date | Progress (%)
Project Overview - Real-Time Tracking Dashboard for Home Management
Project ID | Project Name | Description | Status | Priority | Assigned To | Budget (USD) | Scheduled Start Date | Scheduled End Date | Progress (%) (Target: 100%)
Active Projects
PRJ-001 | Renovation - Kitchen Upgrade | Replace cabinets, install quartz countertops, upgrade appliances. | In Progress | High | Mike Johnson | $12,500.00 | 2024-11-15 | 2024-12-30 | 78%
Next milestone: Install lighting fixtures - Due Dec 10, 2024
PRJ-002 | Smart Home Integration | Install smart thermostats, lights, and security system. | In Progress | Medium | Lisa Chen | $3,800.00 | 2024-11-20 | 2025-01-15 | 45%
Next milestone: Integrate with mobile app - Due Dec 5, 2024
PRJ-003 | Landscaping & Garden Expansion | Add new flower beds, install irrigation system, build stone pathway. | Pending Start | Low | Tom Wilson | $4,200.00 | 2025-01-15 | 2025-03-31 | 8%
Next milestone: Purchase soil & plants - Due Jan 10, 2025
Completed Projects (Last Quarter)
PRJ-004 | Bathroom Remodel - Master Suite | Replace tiles, update shower system, install double vanity. | Completed | High | Sarah Patel | $9,400.00 | 2024-10-15 | 2024-11-30 | 100%
Final review completed - client satisfaction score: 9.8/10
PRJ-005 | Energy Efficiency Upgrade | Install solar panels, upgrade insulation, replace HVAC system. | Completed | High | James Reed | $28,000.00 | 2024-11-30 | 2025-01-31 | 105%
Completed ahead of schedule and under budget by $3,000
Overall Summary: 2 Active ¦ 2 Completed ¦ Total Budget: $57,900.00
Created by: Home Management System - Manager View v2.0 |  |  |  |  | Last Updated: December 3, 2024