## Worksheet
Home Management - Quarterly Project Tracker
Q1 2024 (January - March)
Project Name | Category | Start Date | End Date | Owner | Budget ($) | Status | Notes / Updates
Living Room Renovation | Interior Design | Jan 5, 2024 | Mar 15, 2024 | Jane Smith | 3,500 | Completed | New flooring and paint applied. On schedule.
Kitchen Appliance Upgrade | Appliances | Jan 10, 2024 | Feb 28, 2024 | John Doe | 4,800 | Completed | New oven and microwave installed. Energy efficient.
Garage Organization System | Storage & Organization | Feb 1, 2024 | Apr 5, 2024 | Sarah Lee | 1,200 | In Progress | Shelving and storage bins installed halfway.
Lawn & Garden Makeover | Gardening & Landscaping | Mar 1, 2024 | May 10, 2024 | Mike Brown | 3,000 | In Progress | Grass seeding and flower beds planted.
Smart Home Integration | Technology | Mar 15, 2024 | Jun 30, 2024 | Lisa Wang | 6,500 | Delayed | Waiting on device delivery. Estimated resumption in April.
Q2 2024 (April - June)
Insulation Upgrade | Energy Efficiency | Apr 10, 2024 | May 30, 2024 | Daniel Kim | 5,800 | In Progress | Attic insulation being installed. On track.
Home Security System Update | Safety & Security | May 5, 2024 | Jun 15, 2024 | Amy Chen | 3,100 | Completed | New cameras and sensors installed.
Total Budget (Q1 + Q2) |  |  |  |  | 30,700 | Summary: 4 completed, 3 in progress, 1 delayed