## Worksheet
Inventory Control - Advanced Gantt Chart
Task | Start Date | End Date | Duration (Days) | Responsible | Progress | Status
Raw Material Procurement | 2024-01-05 | 2024-01-15 | 10 | Jane Doe (Purchasing) |  | In Progress
Quality Inspection | 2024-01-16 | 2024-01-25 | 9 | Mike Lee (QA) |  | In Progress
Storage & Labeling | 2024-01-26 | 2024-01-31 | 5 | Sarah Chen (Logistics) |  | In Progress
Inventory Reconciliation | 2024-02-01 | 2024-02-10 | 9 | Daniel Kim (Audit) |  | In Progress
Stock Replenishment Planning | 2024-02-11 | 2024-02-15 | 4 | Lisa Parker (Planning) |  | Completed
System Update & Sync | 2024-02-16 | 2024-02-18 | 3 | Ryan White (IT) |  | In Progress
Final Review & Approval | 2024-02-19 | 2024-02-19 | 1 | Amanda Brown (Manager) |  | Delayed