## Worksheet
Inventory Control - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
INV-001 | Receive Raw Materials | 2024-04-05 | 2024-04-15 | In Progress | 75%
INV-002 | Quality Inspection | 2024-04-16 | 2024-04-19 | In Progress | 68%
INV-003 | Storage Allocation | 2024-04-20 | 2024-04-25 | Pending | 15%
INV-004 | Inventory Update & Verification | 2024-04-26 | 2024-05-15 | Pending | 5%
M-001 | Q3 Inventory Audit | 2024-05-16 | 2024-05-17 | Milestone Reached | 100%
INV-005 | Forecast & Replenishment Planning | 2024-05-18 | 2024-06-30 | Pending | 1%
INV-006 | Update System Records | 2024-07-01 | 2024-07-15 | Pending | 3%