## Worksheet
Inventory Control - Large Business Gantt Chart
Project Timeline & Task Progress Overview ¦ Q3 2024
Task ID | Task Description | Start Date | Due Date | Progress | Status / Notes
INV-AUD-01 | Conduct Physical Inventory Audit (All Warehouses) | 2024-07-01 | 2024-07-15 |  | Completed¦ All locations verified
INV-REC-02 | Reconcile Physical vs System Inventory Records | 2024-07-16 | 2024-07-31 |  | Ongoing¦ Final adjustments pending
INV-SSO-03 | Review & Adjust Safety Stock Levels per SKU | 2024-08-01 | 2024-08-15 |  | Ongoing¦ High-velocity items reviewed
INV-WHR-04 | Redesign Storage Layout for Efficiency Improvements | 2024-08-16 | 2024-09-15 |  | Ongoing¦ Design phase in progress
INV-SYS-05 | Implement New Inventory Module (ERP Integration) | 2024-09-16 | 2024-11-30 |  | Ongoing¦ Requirements finalization
INV-TRN-06 | Train Staff on New Inventory Protocols & Tools | 2024-12-01 | 2024-12-31 |  | Delayed¦ Vendor scheduling issues
INV-FIN-07 | Milestone: Final Audit & Executive Approval | 2024-12-31 | 2024-12-31 |  | Milestone¦ Scheduled for Q4 review