## Worksheet
Inventory Control - Manager View Gantt Chart
Task ID | Task Name | Description | Start Date | End Date | Status | Progress (%)
T001 | Raw Material Procurement | Order and receive raw materials for production line A | 2024-04-15 | 2024-05-10 | In Progress | 65%
T002 | Inventory Audit Q1 | Physical count and reconciliation of all warehouse inventory | 2024-04-18 | 2024-05-05 | Completed | 100%
T003 | Warehouse Reorganization | Rearrange storage layout for improved efficiency and safety | 2024-04-25 | 2024-05-17 | In Progress | 85%
T004 | Supplier Performance Review | Evaluate delivery timelines and quality of current suppliers | 2024-05-15 | 2024-06-30 | Delayed | 25%
T005 | System Upgrade - Inventory Module | Implement new inventory management features in ERP system | 2024-06-15 | 2024-07-31 | In Progress | 45%