## Worksheet
Inventory Control - Multi-Page Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
INV-001 | Raw Material Procurement | 2023-10-05 | 2023-11-15 | 42 | 78%
INV-002 | Quality Inspection | 2023-11-16 | 2023-11-30 | 15 | 95%
INV-003 | Inventory Receiving & Storage | 2023-12-01 | 2023-12-15 | 15 | 48%
INV-004 | Barcode Labeling & Tracking Setup | 2023-12-16 | 2023-12-31 | 16 | 55%
INV-005 | Digital Inventory Audit | 2024-01-01 | 2024-01-31 | 31 | 75%
INV-006 | Stock Reconciliation | 2024-02-01 | 2024-02-15 | 15 | 87%
INV-007 | Reporting & Forecasting | 2024-02-16 | 2024-03-15 | 31 | 35%
INV-008 | System Integration (ERP) | 2024-03-16 | 2024-04-15 | 31 | 65%
INV-009 | Final Audit & Closure | 2024-04-16 | 2024-05-31 | 46 | 89%
INV-010 | Performance Review & Optimization | 2024-06-01 | 2024-07-31 | 61 | 53%
Page 1 of 3
Inventory Control - Multi-Page Gantt Chart (Continued)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
INV-011 | Supplier Performance Evaluation | 2024-08-01 | 2024-08-31 | 31 | 67%
INV-012 | Inventory Turnover Analysis | 2024-09-01 | 2024-10-31 | 61 | 58%
INV-013 | Safety Stock Optimization | 2024-11-01 | 2024-12-31 | 92 | 73%
INV-014 | Seasonal Demand Planning | 2025-01-01 | 2025-03-31 | 91 | 45%
INV-015 | Warehouse Layout Redesign | 2025-04-01 | 2025-06-30 | 91 | 88%
INV-016 | Automated Reordering Setup | 2025-07-01 | 2025-10-31 | 123 | 64%
INV-017 | Staff Training & Onboarding | 2025-11-01 | 2026-01-31 | 93 | 47%
INV-018 | System Upgrade & Maintenance | 2026-02-01 | 2026-05-31 | 123 | 89%
INV-019 | Annual Inventory Review | 2026-06-01 | 2026-12-31 | 184 | 75%
INV-020 | Long-Term Strategy Planning | 2027-01-01 | 2035-12-31 | 3,654 | 9%
Page 2 of 3
Inventory Control - Multi-Page Gantt Chart (Final Page)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
End of Gantt Chart Data
Page 3 of 3
Prepared by:Inventory Management Team
Date:October 5, 2023