## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Raw Material Procurement | 2024-01-01 | 2024-01-15 | 15 | In Progress
Production Setup | 2024-01-16 | 2024-01-25 | 10 | In Progress
Manufacturing Phase 1 | 2024-01-26 | 2024-02-10 | 16 | Pending
Quality Inspection | 2024-02-11 | 2024-02-15 | 5 | Pending
Packaging & Labeling | 2024-02-16 | 2024-02-18 | 3 | Pending
Storage Allocation | 2024-02-19 | 2024-02-19 | 1 | Pending
Final Inventory Check | 2024-02-20 | 2024-02-21 | 2 | Pending
Total Duration: |  |  | 52 Days