## Inventory Control - Gantt Chart
Inventory Control - Gantt Chart
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Gantt Progress Timeline (Weeks)
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6
INV-001 | Inventory Audit - Warehouse A | John Smith | On Track | 2024-03-18 | 2024-03-31
INV-002 | Stock Reconciliation - Inventory B | Emily Chen | On Track | 2024-03-19 | 2024-04-05
INV-003 | Cycle Counting - High Value Items | Robert Johnson | Delayed | 2024-03-20 | 2024-04-15
INV-004 | Data Entry & Validation | Lisa Wong | Completed | 2024-03-15 | 2024-03-18
INV-005 | Report Generation & Review | Michael Brown | In Progress | 2024-03-25 | 2024-04-19
Prepared on March 15, 2024 ¦ Version 1.0 ¦ Inventory Control Department