## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Responsible
T001 | Raw Material Procurement | 2024-01-15 | 2024-01-30 | 16 | Completed | John Doe
T002 | Quality Inspection | 2024-01-31 | 2024-02-05 | 6 | In Progress | Jane Smith
T003 | Warehouse Receiving | 2024-02-06 | 2024-02-15 | 10 | Delayed | Mike Brown
T004 | Inventory Setup in System | 2024-02-16 | 2024-02-18 | 3 | Not Started | Lisa Wong
T005 | Final Audit & Reporting | 2024-02-19 | 2024-02-21 | 3 | Not Started | Robert Taylor
Total Duration: |  |  |  | 38 days