## Worksheet
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | Prioritization Level
INV-001 | Conduct Inventory Audit - Phase I | Inventory Team A | 2024-05-15 | 2024-05-28 | Ongoing | High
INV-002 | Update ERP Inventory Module | IT Integration Team | 2024-05-18 | 2024-06-15 | Ongoing | High
INV-003 | Implement Barcode Scanning System | Operations & IT Team | 2024-06-15 | 2024-07-15 | Delayed | Medium
INV-004 | Train Staff on New Inventory Procedures | HR & Training Department | 2024-07-16 | 2024-07-31 | Completed | Medium
INV-005 | Final System Integration Testing | QA & IT Team | 2024-08-01 | 2024-08-15 | Completed | High
INV-006 | Go-Live & Full Operational Deployment | All Departments | 2024-08-16 | 2024-08-31 | Delayed | High
INV-007 | Post-Implementation Review & Optimization | Project Management Office | 2024-09-01 | 2024-11-30 | Completed | Low
Generated on:¦ This is a dynamic template for Inventory Control Project Planning.