## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Responsible Person
P001 | Project Initiation | 2023-10-01 | 2023-10-05 | 5 | In Progress | Fred Johnson
P002 | Inventory Audit Preparation | 2023-10-06 | 2023-10-15 | 10 | Not Started | Sarah Lee
P003 | Data Collection & Validation | 2023-10-16 | 2023-10-25 | 10 | In Progress | Mike Chen
P004 | System Integration Testing | 2023-10-26 | 2023-11-05 | 11 | Not Started | Amy Patel
P005 | Final Review & Approval | 2023-11-06 | 2023-11-10 | 5 | Not Started | Daniel Kim
P006 | Closure & Documentation | 2023-11-11 | 2023-11-15 | 5 | Not Started | Lisa Wong