## Worksheet
ANNUAL PROJECT PLAN - INVENTORY CONTROL
Project ID | Task Description | Responsible Party | Q1 Start Date | Q1 End Date | Q2 Start Date | Q2 End Date < th > Q3 End Date < / th > < th > Q4 Start Date < / th > < th > Q4 End Date< /th> | Status
INV-2025-001 | Inventory System Audit & Assessment | John Smith, IT Lead | Jan 1, 2025 | Mar 31, 2025 | -- | -- | < th > -- th > < th > -- th > < th > -- th >Pending
INV-2025-002 | Barcode Implementation Phase 1 | Sarah Johnson, Operations | Apr 1, 2025 | < th > Jun 30, 2025 th > < th > -- th > < th > -- th > < th > -- < / td>In Progress
INV-2025-003 | RFID Integration Pilot | Mike Brown, Logistics | Jul 1, 2025 | < th > Sep 30, 2025 th > < th > -- th > < th > -- th > < th > -- < / td>Not Started
INV-2025-004 | Inventory Reconciliation & Reporting Setup | Linda Davis, Finance | Oct 1, 2025 | < th > Dec 31, 2025 th > < th > -- th > < th > -- < / td>Pending
Total Tasks: 4 | [7 empty] | Completed: 0 | In Progress: 1 | Not Started: 3