## Worksheet
Inventory Control - Project Plan
Task ID | Task Name | Description | Responsible Team | Start Date | End Date | Status | Budget (USD)
ICP-001 | Inventory Audit Initiation | Conduct initial assessment of current inventory levels and discrepancies. | Operations Team | 2024-01-05 | 2024-01-15 | In Progress | $8,500
ICP-002 | Data Standardization Setup | Implement uniform data formats and coding standards for inventory records. | IT & Data Team | 2024-01-16 | 2024-01-31 | To Do | $5,750
ICP-003 | System Integration Testing | Test integration between inventory system and ERP platform. | IT Team | 2024-02-01 | 2024-02-15 | To Do | $11,300
ICP-004 | Staff Training Program | Deliver training sessions on new inventory procedures and tools. | HR & Operations | 2024-02-16 | 2024-03-15 | To Do | $7,800
ICP-005 | Pilot Implementation Phase | Roll out inventory system in one warehouse as pilot program. | Operations Team | 2024-03-16 | 2024-04-30 | To Do | $18,500
ICP-006 | Full Deployment & Review | Deploy system company-wide and conduct post-implementation review. | All Departments | 2024-05-01 | 2024-06-30 | To Do | $35,250
Project Overview:This project plan outlines the structured approach to improving inventory control through standardized processes, system integration, and staff training. The goal is to reduce stock discrepancies by at least 90% within six months of full deployment.
Total Project Budget:$87,100
Expected Completion Date:June 30, 2024