## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Assigned To(Responsible)(Role)
001 | Project Initiation | 2023-10-01 | 2023-10-05 | 5 | In Progress | John Doe (Project Manager)
002 | Requirements Gathering(Inventory System Needs) | 2023-10-06 | 2023-10-15 | 10 | To Do | Jane Smith (Business Analyst)
003 | Design Phase - System Architecture(Inventory Control Framework) | 2023-10-16 | 2023-10-25 | 10 | To Do | Mike Brown (System Architect)
004 | Development - Core Modules (Stock Tracking, Reorder Alerts) | 2023-10-26 | 2023-11-15 | 21 | In Progress | Lisa Wong (Software Developer)
005 | Testing Phase - Unit & Integration Testing | 2023-11-16 | 2023-11-30 | 15 | To Do | Robert Kim (QA Engineer)
006 | User Acceptance Testing (UAT) | 2023-12-01 | 2023-12-15 | 15 | To Do | All Stakeholders (Department Managers)
007 | Deployment to Production Environment | 2023-12-16 | 2023-12-18 | 3 | To Do | Tom Davis (DevOps Engineer)
008 | Post-Implementation Review & Documentation | 2023-12-19 | 2023-12-25 | 7 | To Do | Sarah Lee (Documentation Lead)