## Worksheet
INVENTORY CONTROL - DETAILED PROJECT PLAN
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | % Complete | Budget (USD) | Actual Cost (USD) | Memo / Notes
TASK-001 | Define Inventory Scope and Objectives | Project Manager | 2024-04-01 | 2024-04-15 | In Progress | 75% | $1,500.00 | $1,238.50 | Align with procurement and warehouse teams.
TASK-002 | Conduct Current Inventory Audit | Warehouse Supervisor | 2024-04-16 | 2024-05-15 | To Do | 0% | $3,800.00 | $-- | Include all storage areas and sub-inventory locations.
TASK-003 | Implement Inventory Tracking System (Barcode) | IT & Logistics Team | 2024-05-16 | 2024-07-31 | To Do | 0% | $18,500.00 | $-- | Integration with ERP system required.
TASK-004 | Train Staff on New Inventory Procedures | Training Coordinator | 2024-08-01 | 2024-08-15 | To Do | 0% | $5,250.00 | $-- | Schedule sessions for all warehouse personnel.
Summary Metrics: | [7 empty] | Overall Progress: 18%
Generated on¦ This document is confidential and intended solely for authorized personnel.