## Worksheet
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | % Complete | Budget (USD) | Actual Cost (USD)
Phase 1: Project Initiation & Planning
PLN-001 | Define Inventory Control Objectives | Project Manager | 2024-04-01 | 2024-04-15 | In Progress | 85% | $1,500.00 | $1,275.00
PLN-002 | Stakeholder Identification & Engagement | Team Lead | 2024-04-16 | 2024-04-30 | Pending Approval | 15% | $3,500.00 | $525.00
Phase 2: System Design & Development
DES-001 | Design Inventory Tracking Workflow | Systems Analyst | 2024-05-01 | 2024-05-15 | Pending Start | 0% | $7,800.00 | $39.88
DES-002 | Develop Database Schema for Inventory Items | Database Engineer | 2024-05-16 | 2024-06-15 | Pending Start | 0% | $8,950.00 | $13.43
Phase 3: Implementation & Testing
IMP-001 | Deploy Inventory Management Module | IT Team Lead | 2024-06-16 | 2024-07-31 | Pending Start | 0% | $15,500.00 | $98.45
Phase 4: Training & Go-Live
TRN-001 | Conduct User Training Sessions | Training Coordinator | 2024-08-01 | 2024-08-15 | Pending Start | 0% | $5,675.00$34.17
Phase 5: Evaluation & Project Closure
CLO-001 | Final System Performance Review | Project Manager | 2024-08-16 | 2024-08-31 | Pending Start0%$3,500.00$17.58
Total Project Budget: | [7 empty] | $52,925.00
Total Actual Spend to Date: | [7 empty] | $2,386.51