## Worksheet
Inventory Control - Project Plan Template
Template Type:Project Plan ¦Style/Version:Freelancer ¦Purpose:Inventory Control
ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
001 | Conduct Inventory Audit | Jane Smith | 2023-10-05 | 2023-10-15 | In Progress | $850.00
002 | Update Inventory Database | Mark Johnson | 2023-10-16 | 2023-10-25 | In Progress | $1,450.00
003 | Implement Barcode System | Lisa Wong | 2023-10-26 | 2023-11-15 | Delayed | $4,800.00
004 | Train Staff on New System | Alex Rivera | 2023-11-16 | 2023-11-30 | Completed | $750.00
005 | Set Up Automated Reordering System | Sophie Kim | 2023-12-01 | 2023-12-15 | In Progress | $6,900.00
006 | Final System Testing & Validation | Daniel Brooks | 2023-12-16 | 2024-01-15 | In Progress | $3,650.00
Total Budget: | [5 empty] | $18,400.00
Freelancer Style Project Plan Template - Inventory Control System ¦ Last Updated: October 2023