## Worksheet
Inventory Control - Project Plan (Manager View)
Task ID | Task Description | Responsible Team | Status | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Budget (USD)
INV-001 | Inventory Audit & Data Verification | Operations Team | In Progress | 2024-10-05 | 2024-10-15 | 2024-10-06 | — | $8,500
INV-002 | Warehouse Reorganization & Labeling | Fulfillment Team | Pending | 2024-10-16 | 2024-10-30 | — | — | $15,300
INV-003 | Update Inventory Management System (IMS) | IT Support Team | In Progress | 2024-10-15 | 2024-11-05 | 2024-10-16 | — | $38,750
INV-004 | Staff Training on New Inventory Protocols | HR & Training Team | Pending | 2024-11-06 | 2024-11-15 | — | — | $9,800
Total Project Budget: | [7 empty] | $72,350