## Worksheet
Inventory Control - Project Plan
Multi-Page Template for Comprehensive Inventory Management & Planning
Task ID | Task Name | Responsible Person | Timeline |  |  | Status
|  |  | Start Date | End Date | Duration (Days)
T001 | Inventory Audit Preparation | Jane Smith | 2023-10-05 | 2023-10-15 | 11 | Pending
T002 | Data Collection & System Entry | Mike Johnson | 2023-10-16 | 2023-11-30 | 45 | In Progress
T003 | Categorization & Labeling of Items | Sarah Lee | 2023-11-01 | 2023-11-25 | 25 | In Progress
T004 | Software Integration Testing | David Brown | 2023-12-01 | 2023-12-15 | 15 | Pending
T005 | User Training Sessions (Phase 1) | Emily Davis | 2023-12-16 | 2023-12-31 | 16 | Pending
T006 | Final System Validation & Approval | Robert Wilson | 2024-01-01 | 2024-01-15 | 15 | Pending
T007 | Go-Live & Monitoring (Phase 1) | Jane Smith | 2024-01-16 | 2024-01-31 | 16 | Pending
T008 | Performance Review & Feedback Collection | Sarah Lee | 2024-02-01 | 2024-02-15 | 15 | Pending
Total Duration: |  |  | 207 days (approx. 6.9 months)
Category | Item Type | Inventory Metrics
|  | Current Stock Level | Reorder Point (ROP) | Lead Time (Days) | Unit Cost ($)
Raw Materials | Metal Alloys | 240 units | 180 units | 7 days | $45.50
Raw Materials | Plastic Resins | 1,800 units | 1,200 units | 5 days | $12.75
Components | Circuit Boards (Standard) | 980 units | 600 units | 14 days | $27.80
Components | Sensors (High Precision) | 320 units | 150 units | 21 days | $89.95
Finished Goods | Product A (Base Model) | 670 units | 400 units | 3 days | $198.25
Finished Goods | Product B (Premium Model) | 240 units | 180 units | 5 days | $345.90
Maintenance & Consumables | Tooling Supplies (Standard) | 1,100 units | 800 units | 2 days | $6.45
Maintenance & Consumables | Cleaning Kits (Eco-Friendly) | 370 units | 250 units | 4 days | $18.50
Total Items: |  | 6,790 units | 4,430 units | — | $—
Risk ID | Risk Description | Impact & Likelihood |  | Mitigation Strategy
|  | Impact (1–5) | Likelihood (1–5)
R001 | Supplier delay in raw material delivery | 4 | 3 | Diversify suppliers; maintain safety stock of 20%
R002 | Data entry errors during audit process | 3 | 4 | Implement double-entry verification and automated validation checks
R003 | Inadequate user training leading to software misuse | 4 | 2 | Schedule mandatory training sessions with follow-up assessments
R004 | System integration failure with existing ERP | 5 | 3 | Hire third-party specialists for integration; conduct sandbox testing phase
R005 | Downtime during system go-live impacting production flow | 5 | 2 | Perform rollout in phases; schedule during low-production window (weekend)
R006 | Loss of inventory data due to system crash | 5 | 2 | Implement daily cloud backups with automatic recovery protocols
R007 | Cybersecurity vulnerability in inventory database | 4 | 3 | Deploy encryption, multi-factor authentication, and monthly penetration testing
R008 | Skill gap in staff managing new inventory system | 3 | 4 | Assign mentors; create internal knowledge base and SOPs documentation
Total Risks Identified: |  | 8 risks assessed |  |  | —
Phase | Key Deliverables | Resource Allocation
|  | Team Members (Roles) | Estimated Hours | Budget ($)
Phase 1: Planning & Setup | Finalized project scope, team assignment, audit checklist | Mike Johnson (PM), Sarah Lee (Ops), David Brown (IT) | 45 hours | $3,200
Phase 2: Data Collection & Entry | Complete inventory database with 18,500+ items | Jane Smith (Audit Lead), Emily Davis (Training) | 120 hours | $9,600
Phase 3: System Integration & Testing | Verified system integration with ERP and automated workflows | David Brown (IT), Robert Wilson (QA) | 180 hours | $14,400
Phase 4: Training & Rollout | 75% staff trained; go-live completed with minimal downtime | Emily Davis (Training), Jane Smith (PM) | 90 hours | $7,200
Phase 5: Post-Launch Monitoring | Performance reports, feedback analysis, system optimization plan | Sarah Lee (Ops), Robert Wilson (QA) | 60 hours | $4,800
Total Project Cost: |  | $39,200