## Worksheet
INVENTORY CONTROL - PROJECT PLAN
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete
Phase 1: Planning & Requirements Gathering
IT-001 | Define inventory control objectives and KPIs | Project Manager, Inventory Team | 2025-04-01 | 2025-04-15 | In Progress | 75%
IT-002 | Capture current inventory processes and pain points | Process Analysts, Operations Team | 2025-04-16 | 2025-04-30 | Pending | 15%
Phase 2: System Design & Configuration
IT-003 | Design new inventory tracking workflow | System Designer, IT Team | 2025-05-01 | 2025-05-14 | Pending | 0%
IT-004 | Configure inventory management software (e.g., SAP, Oracle) | IT Developer, Vendor Support | 2025-05-15 | 2025-06-10 | Pending | 0%
Phase 3: Testing & Deployment
IT-005 | Conduct unit and integration testing of inventory system | QA Team, IT Department | 2025-06-11 | 2025-06-30 | Pending | 0%
IT-006 | Run pilot test in one warehouse location | Operations Manager, Warehouse Staff | 2025-07-01 | 2025-07-14 | Pending | 0%
Phase 4: Training & Go-Live
IT-007 | Develop training materials and conduct sessions for staff | Training Coordinator, HR Team | 2025-07-15 | 2025-07-31 | Pending | 0%
IT-008 | Full system rollout across all warehouses (Go-Live) | All Teams, IT Support | 2025-08-15 | 2025-08-31 | Pending | 0%
Phase 5: Monitoring & Optimization
IT-009 | Monitor system performance and KPIs for first 3 months | Data Analyst, Project Manager | 2025-09-01 | 2025-11-30 | Pending | 0%
Total Project Duration: | [5 empty] | 2025-04-01 to 2025-11-30