## Worksheet
Inventory Control - Project Plan
Task ID | Task Description | Responsible Team | Status | Start Date | End Date | Budget (USD)
IC-001 | Inventory Audit & Data Validation | Operations Team | In Progress | 2024-05-15 | 2024-05-31 | $8,500.00
IC-002 | System Integration (ERP & Barcode) | IT Department | To Do | 2024-06-01 | 2024-06-15 | $15,750.00
IC-003 | Warehouse Layout Optimization | Fulfillment Team | In Progress | 2024-05-20 | 2024-06-10 | $5,300.00
IC-004 | Staff Training & SOP Development | HR & Operations | To Do | 2024-06-16 | 2024-06-30 | $3,850.00
IC-005 | Pilot Run & Feedback Collection | Quality Assurance | Not Started | 2024-07-01 | 2024-07-15 | $6,200.00
Total Estimated Cost: | [5 empty] | $45,600.00
Project Overview
Objective:Implement a streamlined inventory control system to reduce stock discrepancies by 95% and improve fulfillment accuracy.
Status:Phase 1 in progress (Data audit & warehouse optimization).
Project Duration:May 15, 2024 – July 31, 2024