## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD)
Inventory Control - Project Plan (Planning View)
IC-001 | Conduct Inventory Audit | Jane Smith | 2024-06-01 | 2024-06-15 | In Progress | $3,500.00
IC-002 | Update Inventory Database | Mike Johnson | 2024-06-16 | 2024-07-15 | Not Started | $5,800.00
IC-003 | Implement Barcode Scanning System | Sarah Lee | 2024-07-16 | 2024-08-31 | Not Started | $15,750.00
IC-004 | Train Staff on New System | David Brown | 2024-09-01 | 2024-09-15 | Not Started | $3,600.00
IC-005 | Review and Optimize Inventory Levels | Jane Smith | 2024-11-01 | 2024-11-30 | Not Started | $4,500.00
Total Budget: | [5 empty] | $33,150.00
Generated on: