## Worksheet
Inventory Control - Quarterly Project Plan
Quarter:Q1 2024 ¦Status:In Progress ¦Last Updated:April 5, 2024
# | Task Name | Description | Responsible Team Member | Start Date | End Date | Status | Budget Allocated (USD)
1 | Inventory Audit - Q1 Review | Conduct comprehensive physical and digital inventory audit. | Sarah Johnson | 2024-01-05 | 2024-01-15 | In Progress | $3,500
2 | Warehouse Reorganization | Rearrange storage layout for improved efficiency. | Mike Reynolds | 2024-01-16 | 2024-01-31 | Completed | $7,800
3 | System Upgrade Implementation | Deploy new inventory management software. | Lisa Chen | 2024-02-01 | 2024-02-15 | Completed | $18,500
4 | Staff Training Session 1 | Train team on new system features and protocols. | Alex Rivera | 2024-02-16 | 2024-02-28 | In Progress | $1,950
5 | Supplier Performance Evaluation | Analyze supplier delivery times and accuracy. | Emily Torres | 2024-03-01 | 2024-03-15 | Scheduled | $950
6 | Quarterly Forecasting Review | Create inventory demand forecast for Q2. | James Park | 2024-03-16 | 2024-03-31 | Scheduled | $5,500
Total Budget: | [6 empty] | $48,200