## Worksheet
Inventory Control - Project Plan Report Version
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | Budget (USD)
PRJ-001 | Inventory Audit Preparation | Operations Team | 2024-04-01 | 2024-04-05 | In Progress | $1,500.00
PRJ-002 | Data Collection & Entry | Warehouse Staff | 2024-04-06 | 2024-04-15 | To Do | $3,200.00
PRJ-003 | System Integration Testing | IT Department | 2024-04-16 | 2024-04-25 | To Do | $5,800.00
PRJ-004 | Training & Onboarding | HR & Training Team | 2024-04-26 | 2024-05-10 | To Do | $4,100.00
PRJ-005 | Final Review & Approval | Project Manager | 2024-05-11 | 2024-05-17 | To Do | $1,900.00
Total Budget: | [5 empty] | $16,500.00