## Worksheet
Startup Project Plan - Inventory Control
Task ID | Task Name | Responsible Team Member | Start Date | End Date | Status
INV-001 | Conduct Inventory Audit | Operations Team | 2024-04-05 | 2024-04-15 | In Progress
INV-002 | Update Inventory System Database | IT Department | 2024-04-16 | 2024-04-25 | Pending
INV-003 | Implement Barcode Scanning Solution | Logistics Team | 2024-04-26 | 2024-05-10 | To Do
INV-004 | Train Staff on New System | HR & Training Dept. | 2024-05-11 | 2024-05-17 | To Do
INV-005 | Launch Inventory Control System Live | Project Manager | 2024-05-18 | 2024-05-18 | To Do
Total Tasks: |  |  |  |  | 5