## Worksheet
Inventory Control - Project Plan (Team Use)
Task ID | Task Name | Description | Assigned To | Status | Start Date | Due Date | % Complete
T001 | Conduct Inventory Audit | Perform physical count of all warehouse items | John Doe | In Progress | 2024-04-15 | 2024-04-18 | 65%
T002 | Update Inventory System | Synchronize database with audit results | Jane Smith | Not Started | 2024-04-19 | 2024-04-25 | 0%
T003 | Reconcile Discrepancies | Investigate and resolve inventory variances | Alex Johnson | On Hold | 2024-04-26 | 2024-05-03 | 15%
T004 | Implement New Stock Labels | Create and apply barcode labels to all items | Maria Garcia | Not Started | 2024-05-04 | 2024-05-10 | 0%
T005 | Train Team on New System | Conduct training sessions for warehouse staff | Robert Lee | Not Started | 2024-05-11 | 2024-05-15 | 0%
Total Tasks:5 ¦In Progress:1 ¦Completed:0 ¦Pending:4
Last Updated: April 15, 2024