## Worksheet
Inventory Control - Project Plan Template
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
PRJ-001 | Inventory Audit - Phase 1 | Jane Smith | 2024-04-05 | 2024-04-15 | In Progress | $8,500
PRJ-002 | System Integration Testing | Mike Johnson | 2024-04-16 | 2024-05-10 | Pending | $15,300
PRJ-003 | Warehouse Reorganization | Lisa Brown | 2024-05-11 | 2024-05-31 | Not Started | $6,800
PRJ-004 | Data Validation & Reporting Setup | David Lee | 2024-06-01 | 2024-06-15 | In Progress | $7,100
PRJ-005 | Closure & Review Meeting | Sarah Wilson | 2024-06-16 | 2024-06-30 | Pending | $3,500
Purpose:Inventory Control
Template Type:Project Plan
Style/Version:Template Version 1.2