## Worksheet
Inventory Control - Project Timeline (Advanced)
# | Task Name | Timeline |  |  | Responsible Team | Status | Progress Tracking
|  | Start Date | End Date | Duration (days) |  |  | Actual Progress (%) | Expected Progress (%)
1 | Raw Material Procurement | 2024-03-05 | 2024-03-18 | 14 | Purchasing Department | In Progress |  | 80%
2 | Quality Inspection | 2024-03-19 | 2024-03-25 | 7 | QA Team | Pending |  | 0%
3 | Inventory Receiving & Verification | 2024-03-26 | 2024-03-31 | 6 | Warehouse Team | Pending |  | 0%
4 | Storage Allocation & Labeling | 2024-04-01 | 2024-04-05 | 5 | Logistics Team | Pending |  | 0%
5 | Inventory System Update | 2024-04-06 | 2024-04-12 | 7 | IT Department | Pending |  | 0%
6 | Final Audit & Reporting | 2024-04-13 | 2024-04-18 | 6 | Audit Team | Pending |  | 0%
7 | Project Closure & Documentation | 2024-04-19 | 2024-04-25 | 7 | All Teams | Pending |  | 0%
Total Duration: |  |  | 46 days |  |  | Overall Status: | In Progress
Current Project Completion Rate:65%¦ Upcoming Milestone in 4 days