## Worksheet
Inventory Control - Project Timeline - Analysis View
Task ID | Task Name | Responsible Team | Start Date | Target End Date | Actual End Date | Status | Inventory Impact | Notes/Comments
INV-001 | Initial Inventory Audit | Warehouse Team | 2024-01-15 | 2024-01-31 | 2024-01-30 | Completed | High (Baseline established) | Audit completed with 98% accuracy.
INV-002 | Stock Reconciliation | Finance & Logistics | 2024-02-01 | 2024-02-15 | - | In Progress | Medium (Adjustments pending) | Discrepancies in 3 locations under review.
INV-003 | System Integration Update | IT Department | 2024-02-16 | 2024-03-15 | - | In Progress | High (Critical for automation) | Scheduled maintenance window on 03/10.
INV-004 | Warehouse Layout Optimization | Operations Team | 2024-03-16 | 2024-04-15 | - | In Progress | High (Improves efficiency) | Draft approved; implementation begins 03/25.
INV-005 | Supplier Performance Review | Purchasing Department | 2024-04-16 | 2024-05-31 | - | Delayed (Pending) | Low (Post-integration assessment) | Waiting for supplier data access.
INV-006 | Final Audit & Reporting | Audit Committee | 2024-06-01 | 2024-06-15 | - | Delayed (Pending) | High (Final validation) | Dependent on prior task completion.
Project Overview
Total Tasks:6 ¦Completed:1 ¦In Progress:3 ¦Delayed:2
Status Legend: Completed (Green), In Progress (Orange), Delayed (Red)