## Worksheet
Inventory Control - Project Timeline (Business Use)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | Budget Allocation (USD)
T001 | Inventory Audit - Phase 1 | Operations Team | 2024-04-01 | 2024-04-15 | In Progress | $7,500
T002 | Database Migration & Integration | IT Department | 2024-04-16 | 2024-05-15 | Pending | $18,200
T003 | RFID Tag Implementation Pilot | Supply Chain Group | 2024-05-16 | 2024-06-30 | Pending | $15,750
T004 | Staff Training on New System | HR & Ops Coordination | 2024-07-01 | 2024-07-15 | Pending | $6,800
T005 | Full System Rollout & Monitoring | Project Management Office | 2024-07-16 | 2024-08-31 | Pending | $35,000
T006 | Post-Implementation Review & Optimization | Business Analysis Team | 2024-09-01 | 2024-10-31 | Pending | $12,500