## Worksheet
Phase / Task | Start Date | End Date | Status | Responsible Team | Description / Deliverables
Project Kickoff & Requirements Gathering | 2025-04-01 | 2025-04-15 | Completed | Project Management | Clients requirements validated, scope approved.
System Design & Architecture Planning | 2025-04-16 | 2025-04-30 | Completed | IT Architects | Detailed system architecture, database schema defined.
Inventory Module Development | 2025-05-01 | 2025-06-15 | In Progress | Development Team A | Core inventory tracking, barcode integration, real-time sync.
Reporting & Dashboard Integration | 2025-06-16 | 2025-07-10 | Pending | UI/UX & Data Team | Custom reports, KPIs, and real-time dashboards for clients.
User Acceptance Testing (UAT) | 2025-07-11 | 2025-07-31 | Pending | QA & Client Reps | Clients validate all features and provide feedback.
Deployment Preparation & Training | 2025-08-01 | 2025-08-15 | Pending | Implementation Team | System deployment plan, user training materials & sessions.
Go-Live & Production Deployment | 2025-08-16 | 2025-08-16 | Pending | Deployment Team | Main system deployed to production environment.
Total Duration | 2025-04-01 to 2025-08-16 |  | Approx. 138 days (4 months, 1 week)