## Worksheet
Inventory Control - Project Timeline Dashboard
Tracking inventory movements and project milestones in real-time
Task ID | Project Phase | Description | Start Date | Target End Date | Actual End Date | Status
P-001 | Procurement | Order raw materials for Phase 1 production | 2023-10-05 | 2023-11-15 | - | In Progress
P-002 | Production Planning | Finalize production schedule and resource allocation | 2023-11-16 | 2023-11-30 | - | In Progress
P-003 | Manufacturing Execution | Begin production of standard inventory units | 2023-12-01 | 2024-01-15 | - | In Progress
P-004 | Quality Assurance | Conduct full inspection and compliance testing | 2024-01-16 | 2024-01-31 | - | Delayed (Pending)
P-005 | Inventory Receiving & Storage | Receive and store finished units in warehouse | 2024-02-01 | 2024-03-15 | - | Not Started
P-006 | Delivery Coordination | Prepare shipment to distribution centers | 2024-03-16 | 2024-04-15 | - | Not Started