## Worksheet
Inventory Control - Project Timeline (Extended Version)
Phase | Task Name | Description | Start Date | End Date | Status | Assigned To | Budget (USD)
Phase 1: Planning | Define Inventory Requirements | Identify all inventory items, quantities, and storage needs. | 2024-01-05 | 2024-01-15 | Pending | Jane Smith | $8,500
| Develop Inventory Strategy | Create policies for stock levels, reorder points, and cycle counts. | 2024-01-16 | 2024-01-31 | In Progress | Mark Johnson | $9,750
| Finalize Project Scope & Timeline | Review and approve project scope document. | 2024-02-01 | 2024-02-15 | Closed | Lisa Wong | $3,500
Phase 2: Implementation | Procure Inventory Management Software | Select and purchase software for tracking inventory. | 2024-02-16 | 2024-03-15 | Pending | Robert Kim | $18,900
| Configure System & Integrate Data | Set up software modules and import existing inventory data. | 2024-03-16 | 2024-04-15 | In Progress | Sarah Chen | $15,800
| Train Staff on New System | Conduct training sessions for warehouse and supply team. | 2024-04-16 | 2024-05-31 | Pending | Daniel Reed
| Run Pilot Test in Warehouse A | Test system functionality with 10,000 SKUs. | 2024-06-01 | 2024-06-31 | Closed Lisa Wong
Phase 3: Optimization | Analyze Pilot Results & Refine Process | Review performance metrics and adjust system settings. | 2024-07-01 | 2024-07-15 | In Progress Jane Smith
| Expand to Warehouse B & C | Deploy system across all three facilities. | 2024-07-16 | 2024-08-31 | Pending Robert Kim
| Implement Real-Time Tracking & Alerts | Integrate IoT sensors and automated low-stock alerts. | 2024-09-01 | 2024-10-31 | Pending Sarah Chen
Phase 4: Review & Sustain | Final Project Audit & Documentation | Conduct audit and archive all project records. | 2024-11-01 | 2024-11-30 | Pending Lisa Wong
| Establish Ongoing Monitoring & Reporting | Create monthly dashboards and KPIs for inventory health. | 2024-12-01 | 2025-03-31 | Pending Mark Johnson
Total Project Budget: | [6 empty] | $86,250
This extended project timeline is designed for comprehensive inventory control and implementation across multiple facilities. Last Updated: