## Worksheet
Project Timeline - Inventory Control
Task ID | Task Name | Start Date | End Date | Status | Responsible Person | Budget (USD) | % Complete
PT001 | Inventory Audit Initiation | 2024-06-01 | 2024-06-15 | In Progress | Jane Smith | $8,500 | 75%
PT002 | System Integration Testing | 2024-06-16 | 2024-07-15 | Pending | Mike Johnson | $15,300 | 15%
PT003 | Warehouse Reorganization | 2024-07-16 | 2024-08-31 | In Planning | Sarah Lee | $12,750 | 5%
PT004 | Supplier Verification Phase 1 | 2024-08-15 | 2024-09-30 | Not Started | Tony Williams | $7,200 | 0%
PT005 | Final System Validation & Handover | 2024-10-01 | 2024-11-30 | Not Started | Lisa Brown | $9,850 | 0%
Total Project Cost | [5 empty] | $53,600 | Overall Progress: 24%