## Worksheet
INVENTORY CONTROL - PROJECT TIMELINE
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete
T001 | Raw Material Procurement | Purchasing Department | 2024-04-15 | 2024-05-15 | In Progress | 75%
T002 | Quality Inspection Batch 1 | QC Team | 2024-05-16 | 2024-05-31 | Pending | 0%
T003 | Inventory Reconciliation | Warehouse Staff | 2024-06-01 | 2024-06-15 | Pending | 0%
T004 | Production Line Setup | Manufacturing Team | 2024-06-16 | 2024-07-31 | Pending | 0%
T005 | Final Quality Assurance Check | QA Department | 2024-08-15 | 2024-08-31 | Pending | 0%
Total Project Duration: | [5 empty] | 120 Days