## Worksheet
Inventory Control - Project Timeline
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
T001 | Inventory Audit - Phase 1 | Jane Doe | 2024-04-01 | 2024-04-05 | Completed | 100%
T002 | Data Entry & Validation | John Smith | 2024-04-06 | 2024-04-15 | Pending | 35%
T003 | Barcode System Integration | Maria Lopez | 2024-04-16 | 2024-05-10 | Pending | 15%
T004 | Supplier Reconciliation | Robert Kim | 2024-05-11 | 2024-05-18 | Pending | 5%
T005 | Final Review & Sign-off | Jane Doe | 2024-05-19 | 2024-05-31 | Pending | 0%
Report Generated On:April 1, 2024
This is a one-page template for Inventory Control Project Timeline. Data is subject to update.