## Worksheet
Inventory Control - Project Timeline (Personal Use)
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
T001 | Initial Inventory Audit | Jane Doe | 2025-04-01 | 2025-04-05 | In Progress | $1,500.00
T002 | Software Integration Setup | John Smith | 2025-04-06 | 2025-04-12 | Pending | $3,800.00
T003 | Data Migration & Validation | Emily Brown | 2025-04-13 | 2025-04-19 | Not Started | $5,200.00
T004 | User Training Sessions | David Wilson | 2025-04-20 | 2025-04-25 | Not Started | $1,800.00
T005 | System Go-Live & Monitoring | Sarah Taylor | 2025-04-26 | 2025-04-30 | Not Started | $4,100.00
Total Project Cost: | [5 empty] | $16,400.00