## Worksheet
Inventory Control - Project Timeline
Project ID | Task Description | Start Date | End Date | Status | Responsible Team | Budget (USD)
PJ001 | Inventory Audit Preparation | 2023-10-01 | 2023-10-15 | In Progress | Operations Team | $8,500.00
PJ002 | Barcode System Implementation | 2023-10-16 | 2023-11-30 | Not Started | IT Department | $45,000.00
PJ003 | Warehouse Reorganization | 2023-11-15 | 2023-12-15 | Not Started | Fulfillment Team | $24,750.00
PJ004 | Inventory Forecasting Model Development | 2023-12-16 | 2024-01-31 | Not Started | Data Analytics Team | $38,900.00
PJ005 | System Integration & Testing | 2024-02-01 | 2024-03-15 | Not Started | IT & QA Team | $67,500.00
Total Budget: | [5 empty] | $184,650.00