## Worksheet
Inventory Control - Quarterly Project Timeline
Quarter | Task/Activity | Start Date | End Date | Status | Responsible Team
Q1 2024 | Inventory Audit - Initial Assessment | Jan 01, 2024 | Jan 15, 2024 | Completed | Inventory Team
| System Integration Test (WMS) | Jan 16, 2024 | Jan 31, 2024 | In Progress | IT & Logistics
| Stock Reconciliation (Old Inventory) | Feb 01, 2024 | Feb 15, 2024 | Completed | Finance & Inventory
| Update SOPs for Inventory Handling | Feb 16, 2024 | Feb 28, 2024 | In Progress | Operations Team
Q2 2024 | Implement New Barcode System | Mar 01, 2024 | Mar 31, 2024 | Delayed
| Q3 2024 | Warehouse Optimization Phase 1 | Jun 01, 2024 | Jun 30, 2024 | Completed
|  | Q4 2024 | Annual Inventory Audit & Reporting | Sep 01, 2024 | Sep 30, 2024 | Completed
|  |  | Total Tasks: |  |  |  | 16 | Completed: 12 ¦ In Progress: 3 ¦ Delayed: 1