## Worksheet
Inventory Control - Project Timeline (Startup Version)
Task ID | Task Name | Responsible Team | Start Date | End Date | Status | Action Items
T001 | Initial Inventory Audit | Operations Team | 2024-04-05 | 2024-04-15 | Pending | Edit
T002 | System Integration Setup | IT & Dev Team | 2024-04-16 | 2024-05-10 | In Progress | Edit
T003 | Supplier Onboarding Phase 1 | Purchasing Team | 2024-05-11 | 2024-05-31 | In Progress | Edit
T004 | Barcode System Deployment | IT & Logistics Team | 2024-06-01 | 2024-06-15 | Pending | Edit
T005 | Staff Training & Documentation | HR & Ops Team | 2024-06-16 | 2024-06-30 | Pending | Edit
T006 | Go-Live & Final Review | Executive Team | 2024-07-01 | 2024-07-15 | Pending | Edit
Generated on: