## Worksheet
Inventory Control - Project Timeline Template
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete | Notes/Dependencies
IT-001 | Inventory Audit Initiation | Inventory Team | 2024-04-01 | 2024-04-15 | In Progress | 75% | N/A
IT-002 | Data Collection & Validation | Data Analysts | 2024-04-16 | 2024-05-15 | Not Started | 0% | Requires audit results
IT-003 | SAP Integration Testing | IT Department | 2024-05-16 | 2024-06-15 | Not Started | 0% | Pending data validation
IT-004 | User Training Sessions | Training Coordinator | 2024-06-16 | 2024-07-15 | Not Started | 0% | Scheduled post-integration
IT-005 | Go-Live & System Monitoring | Project Manager | 2024-07-16 | 2024-07-31 | Not Started | 0% | N/A
Template Version:1.0
Purpose:Inventory Control
Type:Project Timeline