## Worksheet
Project ID | Task Name | Category | Start Date | End Date | Status | % Complete
Inventory Control System Upgrade - Q3 2024
IC-01 | Requirements Gathering | Planning | 2024-07-01 | 2024-07-15 | In Progress | 75%
IC-02 | System Design & Architecture | Design | 2024-07-16 | 2024-08-15 | In Progress | 65%
IC-03 | Database Schema Implementation | Development | 2024-08-16 | 2024-09-15 | To Do
IC-04 | Inventory Module Coding & Testing | Development | 2024-09-16 | 2024-10-31
Milestone: System Integration Phase (Oct 31, 2024)
IC-05 | Integration Testing | Testing | 2024-11-01
Final Deliverable: Deployment & Handover (Dec 31, 2024)