## Worksheet
Weekly Project Timeline - Inventory Control
Week of | Task / Activity | Responsible Party | Status | Scheduled Start | Scheduled End | Comments / Notes
Week of January 1 - January 7, 2024
January 1 - January 7 | Conduct Inventory Audit (Phase I) | John Smith | Not Started | 2024-01-01 | 2024-01-03 | Preliminary physical count of raw materials.
| Update Inventory Database (Legacy System) | Jane Doe | Not Started | 2024-01-02 | 2024-01-05 | Synchronize historical data from spreadsheets.
| Review Supplier Lead Times | Mike Chen | In Progress | 2024-01-01 | 2024-01-07 | Analyze delivery delays from Q3 2023.
Week of January 8 - January 14, 2024
January 8 - January 14 | Conduct Inventory Audit (Phase II) | John Smith | Not Started | 2024-01-08 | 2024-01-11 | Count finished goods and packaging supplies.
| Implement New Inventory Tracking Software (Pilot) | Lisa Park | Not Started | 2024-01-09 | 2024-01-13 | Setup and test with warehouse team.
| Identify Obsolete Stock Items | Robert Lee | In Progress | 2024-01-08 | 2024-01-14 | List items with no movement in 6+ months.
Week of January 15 - January 21, 2024
January 15 - January 21 | Finalize Inventory Audit Reports | John Smith | Not Started | 2024-01-15 | 2024-01-18 | Analyze discrepancies and prepare summary.
| Train Staff on New System (Session 1) | Lisa Park | Not Started | 2024-01-16 | 2024-01-17 | First group training – warehouse floor staff.
| Adjust Safety Stock Levels Based on Demand Forecast | Sarah Kim | Not Started | 2024-01-15 | 2024-01-21 | Based on Q4 sales data and upcoming campaigns.
Next Review: January 22, 2024