## Worksheet
Project ID | Project Name | Start Date | End Date | Status | Budget (USD) | Inventory Items Count
PJ001 | Warehouse Expansion Project | 2024-01-15 | 2024-06-30 | In Progress | $750,000.00 | 894
Subtasks:
| Site Preparation | 2024-01-15 | 2024-02-15 | Completed | $75,000.00 | 38
| Structural Construction | 2024-02-16 | 2024-04-30 | In Progress | $350,000.00 | 489
| Inventory System Integration | 2024-05-15 | 2024-06-30 | Planned | $175,000.00 | 367
PJ002 | Automated Storage Upgrade | 2024-03-01 | 2024-11-30 | In Progress | $985,000.00 | 765
| Equipment Procurement | 2024-03-15 | 2024-05-15 | In Progress | $398,750.00 | 347
| Racking System Installation | 2024-06-15 | 2024-08-31 | Planned | $475,000.00 | 389
PJ003 | Inventory Audit Initiative | 2024-05-15 | 2024-07-15 | In Progress | $68,300.00 | 987
| Data Collection & Verification | 2024-05-15 | 2024-06-30 | In Progress | $39,800.00 | 987
Total: |  |  |  |  | $1,803,300.00 | 2,646