## Worksheet
Inventory Control - Project Tracker (Summary View)
Project ID | Project Name | Department | Status | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Inventories Tracked | Total Items In Stock | Total Items Reserved | Last Updated By
PRJ-001 | Warehouse Expansion Phase 1 | Operations | Active | 2024-03-15 | 2024-08-30 | 2024-03-18 | - | 75,436 | 98,754 | 12,563 | Jane Doe
PRJ-002 | Inventory System Upgrade | IT Department | Pending Review | 2024-04-10 | 2024-11-30 | - | - | 67,891 | 85,672 | 9,345 | John Smith
PRJ-003 | Supply Chain Audit 2024 | Audit & Compliance | Overdue | 2024-01-15 | 2024-03-31 | 2024-01-18 | 2024-03-31 | 56,789 | 76,543 | 8,976 | Maria Lopez
Total Projects: | [8 empty] | 120,325 | 78,491 | -
Summary by Status: |  |  |  | Active: 1 |  | Pending: 1 |  | Overdue: 1
Last Updated: May 5, 2024 ¦ Data Source: Inventory Management System v3.2