## KPI Monitoring - Gantt Chart
KPI Monitoring - Gantt Chart (Basic Version)
Task ID | Objective / KPI | Owner | Start Date | End Date | Status | % Complete
1.01 | Increase Customer Satisfaction Score (CSAT) | Customer Success Team | 2024-01-05 | 2024-03-31 | In Progress | 65%
1.02 | Reduce Average Response Time to Support Tickets | Support Team | 2024-01-15 | 2024-06-30 | In Progress | 45%
1.03 | Improve Product Retention Rate by 15% | Product Team | 2024-02-01 | 2024-12-31 | In Progress | 35%
M1.01 | Q1 KPI Review Meeting | Leadership | 2024-03-31 | 2024-03-31 | Upcoming | --
1.04 | Launch New Onboarding Flow for Enterprise Clients | Product & Marketing Teams | 2024-04-01 | 2024-06-30 | Not Started | 5%
M1.02 | Q2 KPI Review Meeting | Leadership | 2024-06-30 | 2024-06-30 | Upcoming | --
1.05 | Enhance Data Security Compliance Level to ISO 27001 | Security Team | 2024-05-15 | 2024-11-30 | In Progress | 68%
Gantt Chart Overview (Text-Based)
Time Period:January 2024 – December 2024