## Worksheet
Task | Start Date | End Date | Responsible Team | Status | Progress Timeline (Gantt)
Project Initiation | 2023-10-01 | 2023-10-07 | Project Management | Completed
Requirements Gathering | 2023-10-08 | 2023-10-14 | Business Analysts | In Progress
Design Phase | 2023-10-15 | 2023-10-28 | UX/UI Team | In Progress
Development | 2023-10-29 | 2023-11-17 | Development Team | Pending
Testing & QA | 2023-11-18 | 2023-12-01 | QA Team | Pending
Client Review | 2023-12-02 | 2023-12-08 | Project Manager | Pending
Deployment | 2023-12-09 | 2023-12-15 | DevOps Team | Pending
Post-Launch Support | 2023-12-16 | 2024-01-15 | Support Team | Pending