## Worksheet
KPI Monitoring - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | KPI Target
JanFebMarAprMayJunGantt Progress Bar (Days)
KT-001 | Project Initiation | 2024-01-05 | 2024-01-15 | 11 | Completed | Deliver 3 stakeholder workshops
KT-002 | Requirement Gathering | 2024-01-16 | 2024-02-15 | 31 | In Progress | Collect 50+ business requirements
KT-003 | Design Phase | 2024-02-16 | 2024-03-15 | 31 | Not Started | Finalize UI/UX mockups
KT-004 | Development & Testing | 2024-03-16 | 2024-05-15 | 61 | Not Started | Complete 95% code coverage with unit tests
Total Duration |  |  | 134 days | Overall Progress |  | (46%)