## Worksheet
Project/Task | Owner | Start Date | Target Date | Status | Budget (USD) | Spend to Date (USD) | Gantt Progress
Q1 Product Launch | Marketing Team | 01/01/2024 | 03/31/2024 | In Progress | $75,000 | $58,650
Website Redesign | IT Department | 01/15/2024 | 04/30/2024 | In Progress | $65,000 | $47,315
Customer Acquisition Campaign | Sales Team | 02/01/2024 | 05/31/2024 | In Progress | $95,000 | $68,795
Quarterly Financial Reporting | Finance Department | 03/01/2024 | 03/15/2024 | Completed | $8,500 | $8,500
Employee Training Program | HR Department | 04/01/2024 | 06/30/2024 | In Progress | $55,000 | $39,768
Inventory Optimization | Operations Team | 01/01/2024 | 07/31/2024 | Delayed | $85,000 | $69,953
Total | - | - | - | 5/6 Tasks Complete / In Progress / Delayed | $378,500 | $283,481